## sprint1
Task ID | Task Name | Resonsible | Start Date |  | End Date | Duration | Status | Priority
1 | SPRINT 1
DATA COLLECTION
1 | Identify the Data | Tanaya |  | 2024-12-01 | 2024-12-10 | 10 Days | Done | High
2 | Identify the Source | Tanaya |  | 2024-12-11 | 2024-12-16 | 5 Days | Done | High
|  | Anushka |  | 2024-12-11 | 2024-12-16 | 5 Days | Done | High
3 | Gather Data: | Tanaya |  | 2024-12-16 | 2024-12-26 | 10 days | Done | High
|  | Anushka |  | 2024-12-16 | 2024-12-26 | 10 days | Done | High
4 | Document Metadata | Tanaya |  | 2024-12-27 | 2024-12-28 | 2 day | Done | low
|  | Anushka |  | 2024-12-27 | 2024-12-28 | 2 day | Done | low
DATA PREPROCESSING
1 | Understand the Data | Tanaya |  | 2024-12-29 | 2024-12-31 | 3 days | Done | High
|  | Anushka |  | 2024-12-29 | 2024-12-31 | 3 days | Done | High
2 | Handle Missing Data | Tanaya |  | 2024-12-31 | 2025-01-11 | 10 Days | In progress | High
|  | Anushka |  | 2024-12-31 | 2025-01-11 | 10 Days | In Progress | High
|  | Charul |  | 2024-12-31 | 2025-01-11 | 10 Days | In progress | HIgh
3 | Handle Outliers | Tanaya |  | 2024-12-12 | 2025-01-16 | 4 Days | In progress | High
|  | Anushka |  | 2024-12-12 | 2025-01-16 | 4 Days | In progress | High
|  | Charul |  | 2024-12-12 | 2025-01-16 | 4 Days | In progress | High
4 | Encode Categorical Data | Charul |  | 2025-01-17 | 2025-01-21 | 4 Days | In progress | High
|  | Anushka |  | 2025-01-17 | 2025-01-21 | 4 Days | In progress | High
|  | Charul |  | 2025-01-17 | 2025-01-21 | 4 Days | In progress | High
5 | Feature Scaling | Tanaya |  | 2025-01-22 | 2025-01-27 | 6 Days | In progress | High
|  | Anushka |  | 2025-01-22 | 2025-01-27 | 6 Days | In progress | High
|  | Charul |  | 2025-01-22 | 2025-01-27 | 6 Days | In progress | High
6 | Feature Engineering | Tanaya |  | 2025-01-28 | 2025-01-31 | 4 Days | In progress | High
|  | Anushka |  | 2025-01-28 | 2025-01-31 | 4 Days | In progress | High
|  | Charul |  | 2025-01-28 | 2025-01-31 | 4 Days | In progress | High
7 | Data Splitting | Charul |  | 2025-02-01 | 2025-02-03 | 3 days | In progress | High
|  | Anushka |  | 2025-02-01 | 2025-02-03 | 3 days | In progress | High

## sprint 2
Task ID | Task Name | Resonsible | Start Date | End Date | Duration | Status | Priority
SPRINT 2 |  | TRAINING AND EVALUATING MODEL
1 | Training the Model
i. | Select a Model | Dimple | 2025-02-04 | 2025-02-14 | 10 Days | In Progress | High
|  | Aabha | 2025-02-04 | 2025-02-14 | 10 Days | In Progress | High
ii. | Define the Objective Function | Dimple | 2025-02-15 | 2025-02-17 | 2 Days | In Progress | High
|  | Aabha | 2025-02-15 | 2025-02-17 | 2 Days | In Progress | High
iii. | Split the Data | Dimple | 2025-02-18 | 2025-02-19 | 1 Days | In Progress | High
iv. | Initialize the Model | Dimple | 2025-02-19 | 2025-02-28 | 9 days | In Progress | High
| Train the Model | Aabha | 2025-02-19 | 2025-02-28 | 9 days | In Progress | High
v. | Hyperparameter Tuning | Dimple | 2025-03-01 | 2025-03-06 | 5 Days | In Progress | High
|  | Aabha | 2025-03-01 | 2025-03-06 | 5 Days | In Progress | High
2 | Evaluating the Model
i. | Make Predictions | Aabha | 2025-03-07 | 2025-03-10 | 4 Days | In Progress | High
ii | Choose Evaluation Metrics | Aabha | 2025-03-11 | 2025-03-12 | 1 Days | In Progress | High
iii. | Compute Metrics | Aabha | 2025-03-13 | 2025-03-23 | 10 Days | In Progress | High
| Analyze Errors | Dimple | 2025-03-13 | 2025-03-23 | 10 Days | In Progress | High
iv. | Perform Cross-Validation | Dimple | 2025-03-24 | 2025-03-29 | 5 Days | In Progress | High
v. | Compare Models | Dimple | 2025-03-30 | 2025-04-04 | 5 Days | In Progress | High
vi. | Visualize Performance | Dimple | 2025-04-04 | 2025-04-06 | 3 Days | In Progress | High

## sprint 3
Task ID | Task Name | Resonsible | Start Date | End Date | Duration | Status | Priority
| Sprint 3. | 1. Optimizing the Model
1 | Analyze Baseline Performance | Aabha | 2025-04-07 | 2025-04-12 | 5 Days | In Progress | High
|  | Tanaya | 2025-04-07 | 2025-04-12 | 5 Days | In Progress | High
2 | Identify Areas for Improvement | Tanaya | 2025-04-13 | 2025-04-17 | 5 days | In Progress | High
3 | Hyperparameter Tuning | Tanaya | 2025-04-18 | 2025-04-28 | 10 Days | In Progress | High
|  | Aabha | 2025-04-18 | 2025-04-28 | 10 Days | In Progress | High
4 | Feature Engineering | Tanaya | 2025-04-29 | 2025-05-03 | 5 Days | In Progress | High
|  | Aabha | 2025-04-29 | 2025-05-03 | 5 Days | In Progress | High
5 | Use Regularization | Tanaya | 2025-05-04 | 2025-05-11 | 7 Days | In Progress | High
6 | Ensemble Methods | Tanaya | 2025-05-12 | 2025-05-19 | 8 Days | In Progress | High
2. Validating the Model
1 | Cross-Validation | Aabha | 2025-05-20 | 2025-05-30 | 6 Days | In Progress | High
2 | Evaluate Metrics | Aabha | 2025-06-01 | 2025-06-05 | 5 Days | In Progress | High
3 | Visualize Performance | Aabha | 2025-06-06 | 2025-06-11 | 5 Days | In Progress | High
4 | Test Set Evaluation | Aabha | 2025-06-12 | 2025-06-12 | 6 Days | In Progress | High
5 | Statistical Validation | Aabha | 2025-06-13 | 2025-06-16 | 6 Days | In Progress | High

## Sprint 4
Task ID | Task Name | Resonsible | Start Date | End Date | Duration | Status | Priority
| Sprint 4. | UI Designing and Integrate model into application
1 | Define Objectives | Anushka | 2025-06-17 | 2025-06-21 | 5 Days | In Progress | High
2 | Understand User Requirements | Charul | 2025-06-22 | 2025-06-26 | 5 Days | In Progress | High
3 | Plan the UI Workflow | Charul | 2025-06-27 | 31-06-2025 | 5 Days | In Progress | High
4 | Wireframe the Design | Anushka | 2025-07-01 | 2025-07-05 | 5 Days | In Progress | High
5 | Design Components | Anushka | 2025-07-06 | 2025-07-10 | 5 Days | In Progress | High
6 | Add Visual Design | Anushka | 2025-07-11 | 2025-07-15 | 5 Days | In Progress | High
7 | Implement the UI | Anushka | 2025-07-16 | 2025-07-20 | 5 Days | In Progress | High
8 | Integrate the Model | Anushka | 2025-07-21 | 2025-07-25 | 5 Days | In Progress | High
9 | Test the UI | Anushka | 2025-07-26 | 2025-07-30 | 5 Days | In Progress | High
10 | Deploy and Maintain | Anushka | 2025-08-01 | 2025-08-05 | 5 Days | In Progress | High